## Sheet1
System Name: Student Expense Management System
Members: Joseph Nino Amarillo, Emmanuel Dedumo, Ashley Josh Vequiso
Statuses |  | Todo
In-Progress
Done
On-hold
[5 empty] | August |  |  |  | September |  |  |  | October |  |  |  | November
Tasks | Assignee | Date Started | Date Finished | Status | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
1. Document Revision Log | Amarillo,Dedumo,Vequiso | 21/08/2024 | 31/08/2024 | Done
2. Document Reviewers | Amarillo,Dedumo,Vequiso | 21/08/2024 | 31/08/2024 | Done
3. Approver & Signoff | Amarillo,Dedumo,Vequiso | 21/08/2024 | 31/08/2024 | Done
4. Introduction | Amarillo,Dedumo,Vequiso | 21/08/2024 | 31/08/2024 | Done
4.1 Document Purpose | Amarillo,Dedumo,Vequiso | 21/08/2024 | 31/08/2024 | Done
4.2 Document Scope | Amarillo,Dedumo,Vequiso | 21/08/2024 | 31/08/2024 | Done
4.3 Document Audience | Amarillo,Dedumo,Vequiso | 21/08/2024 | 31/08/2024 | Done
4.4 Business Analysis Approach | Amarillo,Dedumo,Vequiso | 21/08/2024 | 31/08/2024 | Done
5. System Architecture & Functional Overview | Amarillo,Dedumo,Vequiso | 21/08/2024 | 31/08/2024 | Done
5.1 Platform Overview and System Components | Amarillo,Dedumo,Vequiso | 21/08/2024 | 31/08/2024 | Done
5.2 Functions Requirements | Amarillo,Dedumo,Vequiso | 21/08/2024 | 31/08/2024 | Done
5.3 Logical Data Model | Amarillo,Dedumo,Vequiso | 21/08/2024 | 31/08/2024 | Done
6. Github | Amarillo,Dedumo,Vequiso | 23/09/2024 | 23/09/2024 | In-progress
6.1 Creating of Repository | Amarillo,Dedumo,Vequiso | 23/09/2024 | 23/09/2024 | In-progress
6.2 Creating of ERD and UI/UX | Amarillo,Dedumo,Vequiso | 23/09/2024 | 23/09/2024 | Done
7. Create Figma | Amarillo,Dedumo,Vequiso | 2024-10-06 | 2024-10-14 | Done
7.1 Login/Logout | Amarillo,Dedumo,Vequiso | 2024-10-06 | 2024-10-14 | Done
7.2 Dashboard | Amarillo,Dedumo,Vequiso | 2024-10-06 | 2024-10-14 | Done
7.3 Add and Manage Expense | Amarillo,Dedumo,Vequiso | 2024-10-06 | 2024-10-14 | Done
7.4 Profile | Amarillo,Dedumo,Vequiso | 2024-10-09 | 2024-10-14 | Done
7.5 Expense Report | Amarillo,Dedumo,Vequiso | 2024-10-11 | 2024-10-14 | Done
7.6 Savings Goal | Amarillo,Dedumo,Vequiso | 2024-10-13 | 2024-10-14 | Done
7.7 Forgot Password Page | Amarillo,Dedumo,Vequiso | 2024-10-13 | 2024-10-14 | Done
7.8 Create Account | Amarillo,Dedumo,Vequiso | 2024-10-13 | 2024-10-14 | Done